## Test Plan
Test Plan
Project:EchoGPT & AppTestingService — Android apps + websites
Tester:Nasir Ahmed
Date: 03/12/2025
Section | Item | Details
Scope | In-scope targets | Android Apps (EchoGPT Chat, AppTestingService), Websites (echogpt.live, apptestingservice.com)
Devices & OS | Android | Medium_Phone_API_36.1
Devices | Browsers | Chrome, Firefox, Edge (latest desktop).
Test Types | Functional | Core flows—install, login, chat, form submission.
| UI / Visual | Layout, alignment, responsive issues, text overlap, icon clarity.
| Accessibility | Color contrast, labels, keyboard focus, alt text.
| Security | Input validation, auth validation, local storage.
| Stability | Background/foreground, long session, rapid navigation, crash checks
| Negative / Edge | Invalid inputs, network off, long text, denied permissions.
| Exploratory | 30–45 min exploratory session on risky or new features
Environment & Tools | Tools Used | Android Studion Emulator, screenshot tool
| Test Data | Valid data, invalid data, large text, special characters, emoji, long messages
| Network | Wi-Fi, 4G/5G, Slow 3G, Offline
Test Data | Input sets | Valid/invalid email/password, special chars, long strings, emojis.
Entry Criteria | Readiness | Apps installed, sites accessible, accounts ready, environment set
Exit Criteria | Completion | ≥25 test cases executed; ≥3 valid bugs with evidence; exploratory notes; summary report
Deliverables | Artifacts | Test Plan, Test Cases, Execution Log, Bug Reports, Exploratory Notes, Summary

## Test Cases
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Severity
TC_RF_001 | (TS_001) Register Functionality | Validate Registering an Account by providing only the Mandatory fields | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log In' 2. Click on 'Create Account' option 3. Enter new Account Details into the Mandatory Fields (First Name, Last Name, E-Mail,phone, Password 4. Click on 'Create account' button . | Not Applicable | 1. User should be logged in, taken to 'Dashboard' page and proper details should be displayed on the page. | 1. User got logged in, taken to 'Account Succcess' page sucessfully and proper details got displayed on the page | High | Major
TC_RF_002 | (TS_001) Register Functionality | Validate 'Thank you for registering' email is sent to the registered email address as a confirmation for registering the account | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log In' 2. Click on 'Create Account' option 3. Enter new Account Details into the Mandatory Fields (First Name, Last Name, E-Mail,phone, Password 4. Click on 'Create account' button . | Not Applicable | 1. Validate a confirmation email for registering the account is sent to the registered email address. | 1. User has not received any email to his registered email address | Medium | Major
TC_RF_003 | (TS_001) Register Functionality | Validate proper notification messages are displayed for the mandatory fields, when you don't provide any fields in the 'Create account' Page | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' button 2. Click on 'Create account' option 3. Don't enter anything into the fields 4. Click on 'Create account' button | Not Applicable | 1. The below warning messages should be displayed for the respective fields: For First Name field, the warning message 'First Name must be between 1 and 32 characters!' should be displayed For E-Mail field, the warning message 'E-Mail Address does not appear to be valid!' should be displayed For phone field, the warning message 'phone must be between 3 and 32 characters!' should be displayed For Password field, the warning message 'Password must be between 4 and 10 characters!' should be displayed | Warning messages were displayed as per the Email and Password, but no validation was applied to the Name and Phone Number fields. | Medium | Major
TC_RF_004 | (TS_001) Register Functionality | Validate Registering an Account by providing the existing account details (i.e. existing email address) | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' button 2. Click on 'Create account' option 3. Don't enter anything into the fields 4. Click on 'Create account' button | First Name - Nasir E-Mail - nasir@gmail.com Telephone - 12345678 Password - 12345678 | 1. Account should not be created again, instead the warning messsage - 'Warning: E-Mail Address is already registered!' should be displayed | 1. Warning messages as specified in the Expected Results got displayed | High | Major
TC_LF_001 | (TS_002) Login Functionality | Validate logging into the Application using valid credentials | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' option 2. Enter valid email address into the 'E-Mail Address' field - 3. Enter valid password into the 'Password' field 4. Click on 'Sign in' button | E-Mail - nasir@gmail.com Password - 12345678 | 1.User should be navigated to Login page 2.User should get logged in and taken to the 'Dashboard' page | 1. User is navigated to Login page 2.User got logged in and taken to the 'Dashboard' page | High | Major
TC_LF_002 | (TS_002) Login Functionality | Validate logging into the Application using invalid credentials (i.e. Invalid email address and Invalid Password) | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' option 2. Enter Invalid email address into the 'E-Mail Address' field - 3. Enter Invalid password into the 'Password' field 4. Click on 'Sign in' button | E-Mail - abcddnasir@gmail.com Password - 383629823 | 1. Warning message comes: Invalid credentials | Warning message with the text 'Warning: Invalid credentials' got displayed | High | Major
TC_DB_001 | (TS_003) Dashboard Functionality | Verify Profile page opens correctly | User must be logged in | 1. Login to app 2. Click on profile icon (top right) 3. Click on “Profile” | Valid user account | Profile page should open successfully without any error | 404 Page Not Found displayed | High | Major
TC_PM_001 | (TS_004) Payment Functionality | Verify error message shown during payment with valid app details | 1. User must be logged in 2. App details must be submitted successfully 3. Payment page must be accessible | 1. Login to the system 2. Go to Dashboard 3. Click on “Submit App” 4. Fill all valid app details 5. Proceed to Payment step 6. Select “Android Basic Testing Package” 7. Select any payment method (Stripe / SSLCommerz) 8. Click on “Checkout” button | Valid app name, valid package selected, valid user login | Payment process should continue to the selected payment gateway without showing any validation error | Payment successfully continues to selected payment gateway without showing any error | Medium | Major
TC_ATS-001 | (TS_005) App package link navigation | Verify "App Package" external link opens valid destination | 1. Open the Application (https://apptestingservice.com/) in any Browser.2. User must be logged in 3. At least one app must be in testing status | 1. Login to the system 2. Go to Dashboard 3. Click on View Sample Dashboard / App Details 4. Scroll to App Package section 5. Click on the package link (com.vanti.mealchaos) | Not Applicable | User should be redirected to the correct app details page or external Play Store link in a new tab | App Package link does not respond / no redirection happens | Low | Minor
TC_CHAT_001 | (TS_006) Business policy verification for chat access | Verify user cannot start chat without signing up | 1. Open the Application (https://echogpt.live/login) in any Browser | 1. Open browser 2. Go to EchoGPT website 3. Do not log in or sign up 4. Try to type a message in chat input 5. Try to send the message | Any random message (e.g., “Hello”) | System should not allow user to chat and should ask the user to sign up or log in | System not allow user to chat and should ask the user to sign up or log in | High | Major
TC_IMG_001 | (TS_007) Image generation | Verify user can generate image after providing prompt | 1. User must have a valid account 2. User must be logged in | 1. Open EchoGPT website 2. Sign in with valid credentials 3. Go to Image generation section 4. Enter valid prompt in image input field 5. Click Generate button | Valid prompt (e.g., “Sunset over mountains”) | System should generate the image corresponding to the entered prompt | System shows error: “failed to generate image try again” | High | Major
TC_CHAT_001 | (TS_007) Verify chat functionality after login | Login and send a new chat message | User has a valid account and is on the website/app login page | 1. Open website/app 2. Login with valid credentials 3. Click on "New Chat" 4. Type a message 5. Click send | Username: testuser Password: Test@123 Message: "Hello" | After sending, the chat message should appear in the chat window and the system should respond with a relevant answer | System responded correctly with an answer to "Hello" | Medium | Major
TC_CHAT_002 | (TS_007) Verify chat functionality after continuous chatting | EchoGPT stops responding after multiple messages | 1. User must be logged in 2. Internet connection must be active | 1. Open EchoGPT website/app 2. Login with valid account 3. Start a new chat 4. Send multiple messages continuously for some time 5. Send another new message | Messages like: "Hi" "How are you?" "Explain testing" "What is bug?" | EchoGPT should respond to every message without stopping | After some time, EchoGPT does not respond to new messages at all | High | Major
TC_DEV_001 | (TS_008) Verify developer account creation | Sign up with valid data and access developer platform | 1. User must have internet connection 2. EchoGPT website must be accessible | 1. Open EchoGPT website 2. Click on API Platform link 3. Redirect to Developer page 4. Click on Login button 5. Click on Sign Up 6. Enter Name, Email, Phone, Password 7. Click on 'Sign Up' | Name: Nasir Email: nasir@test.com Phone: 017XXXXXXXX Password: Test@123 | User should be successfully registered and redirected to the Developer Platform dashboard | User account created successfully and Developer Platform opened | Medium | Minor
TC_DEV_NEG_001 | (TS_009) Register Functionality | Sign up should fail with invalid email | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT website 2. Go to API Platform 3. Go to Developer page 4. Click Login → Sign Up 5. Enter all valid data except email 6. Click Submit | Name: Nasir Email: nasir@123 Phone: 017XXXXXXXX Password: Test@123 | System should show proper error message like “Please enter a valid email address” and should not allow sign up | Warning messages were displayed as per the Email . | High | Major
TC_DEV_NEG_002 | (TS_009) Register Functionality | Sign up should fail when required fields are empty | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT website 2. Go to API Platform 3. Go to Developer page 4. Click Login → Sign Up 5. Keep Name/Phone/Password empty 6. Click "Sign Up' | Name: (Blank) Email: nasir@gmail.com Phone: (Blank) Password: (Blank) | System should show validation message for each required field and should not create account | User account created successfully and Developer Platform opened | High | Major
TC_DEV_NEG_003 | (TS_009) Register Functionality | Sign up should work with valid phone number | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid Name, Email, Phone, Password 5. Click "Sign Up' | Phone: 01712345678 | Account should be created successfully and user should enter Developer Platform | User account created successfully and Developer Platform opened | Medium | Minor
TC_DEV_NEG_004 | (TS_009) Register Functionality | System should not accept short phone number | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid data except Phone 5. Click "Sign Up' | Phone: 0171234 | System should show error like “Enter a valid phone number” | User account created successfully and Developer Platform opened | Medium | Minor
TC_DEV_NEG_005 | (TS_009) Register Functionality | System should not accept special characters | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid data except Phone 5. Click "Sign Up' | Phone: 01712@#678 | System should show error like “Enter a valid phone number” | User account created successfully and Developer Platform opened | Medium | Minor
TC_LOGIN_001 | (TS_010) Login Functionality | User should be able to sign in with existing account | 1. User account must already be created 2. User must be on EchoGPT Login page 3. Internet connection active | 1. Open EchoGPT website 2. Go to API Platform → Developer Page 3. Click on Login 4. Enter valid Email and Password 5. Click on Sign In button | Email: nasir@test.com Password: Test@123 | User should be successfully logged in and redirected to Developer Platform dashboard | 1. User is navigated to Login page | High | Major
TC_AppTestingService_Install_001 | (TS_011) Verify app installation from Play Store | App should install successfully | 1. Internet connection must be active 2. User must be logged into Play Store | 1. Open Play Store 2. Search the App Testing Service app 3. Click Install | Not Applicable | App should be downloaded and installed successfully without any error | App install successfully | High | Major
TC_APP_002 | (TS_011) Verify app launch after installation | App should not crash on launch | 1. App must be installed successfully | 1. Tap on app icon from home screen | Not Applicable | App should open without crashing | App open without crashing | High | Major
TC_APP_003 | (TS_012) Verify first screen loading after app launch | First screen should load properly | 1. App must be installed 2. App must open successfully | 1. Open the app 2. Observe the first screen UI | Not Applicable | First screen should load fully without blank screen, delay, or UI break | First screen load fully without blank screen, delay, or UI break | High | Major
TC_SIGNUP_001 | (TS_013) Verify email field input behavior during sign up | Email input is hidden and automatically filled in password field | 1. User must be on Sign Up page 2. Internet connection active | 1. Open the app/website 2. Go to Sign Up page 3. Click on Email Address field 4. Type a valid email 5. Observe Email field and Password field | Email: nasir@test.com | Email field should display normal text (not masked) and password field should remain empty until user types password manually | Email field shows dots (●●●) like password and the same email is automatically filled into the password field | High | Major
TC_LOGIN_001 | (TS_014) Verify login after manual vs Google sign up | Manual sign up credentials fail to login, Google sign up works | 1. User has manually created account 2. User has Google account sign up 3. Internet connection active | 1. Open app/website 2. Click Login 3. Enter Email + Password from manual sign up 4. Click Sign In 5. Observe result 6. Logout 7. Try login with Google sign up credentials | Manual: Email: zzzz@gmail.com ,Password: 12345 Google: Email: nasir@gmail.com | Manual sign up credentials should login successfully; Google sign up credentials should login successfully | Manual sign up credentials show “Invalid Credentials”; Google sign up credentials login successfully | High | Major
TC_LOGIN_001 | (TS_014) Verify behavior when Google login cancelled | Canceling Google login causes black screen / UI freeze | 1. App installed and on Login page 2. Internet connection active 3. At least one Google account available on device | 1. Open app/website 2. Navigate to Login page 3. Click on Google Login button 4. Google account window appears 5. Press back / cancel without selecting any email 6. Observe UI | Not Applicable | App should return to normal login UI without freeze or black screen | Login UI turns black immediately after cancelling Google login | High | Major
TC_Echo_INSTALL_01 | (TS_014) Verify app installation from Play Store | App should install successfully | 1. Internet connection must be active 2. User must be logged into Play Stor | 1. Open Play Store 2. Search EchoGPT app 3. Click Install | Not Applicable | App should be downloaded and installed successfully without any error | App downloaded and installed successfully without any error | High | Major
TC_LAUNCH_01 | (TS_015) Verify app stability on first launch | App should not crash on first launch | App installed successfully, Internet active | 1. Tap on EchoGPT app icon 2. Observe app behavior on launch | Not Applicable | App should open successfully without crashing | App open successfully without crashing | High | Major
TC_SPLASH_01 | TS_016) Verify first screen loads correctly | Splash / First screen should load without issues | App installed successfully, App launches without crash | 1. Launch app 2. Observe Splash screen and first screen load 3. Check UI elements properly displayed | Not Applicable | Splash screen and first screen should load fully without blank screen, delay, or broken UI | Splash screen and first screen loaded fully without blank screen, delay, or broken UI | High | Major

## Test Cases Execution Resuls
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Severity | Result | Bug Id | Environment | Timestamps
TC_RF_001 | (TS_001) Register Functionality | Validate Registering an Account by providing only the Mandatory fields | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log In' 2. Click on 'Create Account' option 3. Enter new Account Details into the Mandatory Fields (First Name, Last Name, E-Mail,phone, Password 4. Click on 'Create account' button . | Not Applicable | 1. User should be logged in, taken to 'Dashboard' page and proper details should be displayed on the page. | 1. User got logged in, taken to 'Account Succcess' page sucessfully and proper details got displayed on the page | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-03-12
TC_RF_002 | (TS_001) Register Functionality | Validate 'Thank you for registering' email is sent to the registered email address as a confirmation for registering the account | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log In' 2. Click on 'Create Account' option 3. Enter new Account Details into the Mandatory Fields (First Name, Last Name, E-Mail,phone, Password 4. Click on 'Create account' button . | Not Applicable | 1. Validate a confirmation email for registering the account is sent to the registered email address. | 1. User has not received any email to his registered email address | Medium | Major | Fail | APPTESTINGSERVICE_BUG_001 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-03-12
TC_RF_003 | (TS_001) Register Functionality | Validate proper notification messages are displayed for the mandatory fields, when you don't provide any fields in the 'Create account' Page | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' button2. Click on 'Create account' option 3. Don't enter anything into the fields 4. Click on 'Create account' button | Not Applicable | 1. The below warning messages should be displayed for the respective fields: For First Name field, the warning message 'First Name must be between 1 and 32 characters!' should be displayed For E-Mail field, the warning message 'E-Mail Address does not appear to be valid!' should be displayed For phone field, the warning message 'phone must be between 3 and 32 characters!' should be displayed For Password field, the warning message 'Password must be between 4 and 10 characters!' should be displayed | Warning messages were displayed as per the Email and Password, but no validation was applied to the Name and Phone Number fields. | Medium | Major | Fail | APPTESTINGSERVICE_BUG_002 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-03-12
TC_RF_004 | (TS_001) Register Functionality | Validate Registering an Account by providing the existing account details (i.e. existing email address) | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' button 2. Click on 'Create account' option 3. Don't enter anything into the fields 4. Click on 'Create account' button | First Name - Nasir E-Mail - nasir@gmail.com Telephone - 12345678 Password - 12345678 | 1. Account should not be created again, instead the warning messsage - 'Warning: E-Mail Address is already registered!' should be displayed | 1. Warning messages as specified in the Expected Results got displayed | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-03-12
TC_LF_001 | (TS_002) Login Functionality | Validate logging into the Application using valid credentials | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' option 2. Enter valid email address into the 'E-Mail Address' field - 3. Enter valid password into the 'Password' field 4. Click on 'Sign in' button | E-Mail - nasir@gmail.com Password - 12345678 | 1.User should be navigated to Login page 2.User should get logged in and taken to the 'Dashboard' page | 1. User is navigated to Login page 2.User got logged in and taken to the 'Dashboard' page | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-04-12
TC_LF_002 | (TS_002) Login Functionality | Validate logging into the Application using invalid credentials (i.e. Invalid email address and Invalid Password) | 1. Open the Application (https://apptestingservice.com/) in any Browser | 1. Click on 'Log in' option 2. Enter Invalid email address into the 'E-Mail Address' field - 3. Enter Invalid password into the 'Password' field 4. Click on 'Sign in' button | E-Mail - abcddnasir@gmail.com Password - 383629823 | 1. Warning message comes: Invalid credentials | Warning message with the text 'Warning: Invalid credentials' got displayed | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-04-12
TC_DB_001 | (TS_003) Dashboard Functionality | Verify Profile page opens correctly | User must be logged in | 1. Login to app 2. Click on profile icon (top right) 3. Click on “Profile” | Valid user account | Profile page should open successfully without any error | 404 Page Not Found displayed | High | Major | Fail | APPTESTINGSERVICE_BUG_003 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-04-12
TC_PM_001 | (TS_004) Payment Functionality | Verify error message shown during payment with valid app details | 1. User must be logged in 2. App details must be submitted successfully 3. Payment page must be accessible | 1. Login to the system 2. Go to Dashboard 3. Click on “Submit App” 4. Fill all valid app details 5. Proceed to Payment step 6. Select “Android Basic Testing Package” 7. Select any payment method (Stripe / SSLCommerz) 8. Click on “Checkout” button | Valid app name, valid package selected, valid user login | Payment process should continue to the selected payment gateway without showing any validation error | Payment successfully continues to selected payment gateway without showing any error | Medium | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-04-12
TC_ATS-001 | (TS_005) App package link navigation | Verify "App Package" external link opens valid destination | 1. Open the Application (https://apptestingservice.com/) in any Browser.2. User must be logged in 3. At least one app must be in testing status | 1. Login to the system 2. Go to Dashboard 3. Click on View Sample Dashboard / App Details 4. Scroll to App Package section 5. Click on the package link (com.vanti.mealchaos) | Not Applicable | User should be redirected to the correct app details page or external Play Store link in a new tab | App Package link does not respond / no redirection happens | Low | Minor | Fail | APPTESTINGSERVICE_BUG_004 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-04-12
TC_CHAT_001 | (TS_006) Business policy verification for chat access | Verify user cannot start chat without signing up | 1. Open the Application (https://echogpt.live/login) in any Browser | 1. Open browser 2. Go to EchoGPT website 3. Do not log in or sign up 4. Try to type a message in chat input 5. Try to send the message | Any random message (e.g., “Hello”) | System should not allow user to chat and should ask the user to sign up or log in | System not allow user to chat and should ask the user to sign up or log in | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-04-12
TC_IMG_001 | (TS_007) Image generation | Verify user can generate image after providing prompt | 1. User must have a valid account 2. User must be logged in | 1. Open EchoGPT website 2. Sign in with valid credentials 3. Go to Image generation section 4. Enter valid prompt in image input field 5. Click Generate button | Valid prompt (e.g., “Sunset over mountains”) | System should generate the image corresponding to the entered prompt | System shows error: “failed to generate image try again” | High | Major | Fail | ECHOGPT_BUG_005 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_CHAT_001 | (TS_007) Verify chat functionality after login | Login and send a new chat message | User has a valid account and is on the website/app login page | 1. Open website/app 2. Login with valid credentials 3. Click on "New Chat" 4. Type a message 5. Click send | Username: testuser Password: Test@123 Message: "Hello" | After sending, the chat message should appear in the chat window and the system should respond with a relevant answer | System responded correctly with an answer to "Hello" | Medium | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_CHAT_002 | (TS_007) Verify chat functionality after continuous chatting | EchoGPT stops responding after multiple messages | 1. User must be logged in 2. Internet connection must be active | 1. Open EchoGPT website/app 2. Login with valid account 3. Start a new chat 4. Send multiple messages continuously for some time 5. Send another new message | Messages like: "Hi" "How are you?" "Explain testing" "What is bug?" | EchoGPT should respond to every message without stopping | After some time, EchoGPT does not respond to new messages at all | High | Major | Fail | ECHOGPT_BUG_006 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_DEV_001 | (TS_008) Verify developer account creation | Sign up with valid data and access developer platform | 1. User must have internet connection 2. EchoGPT website must be accessible | 1. Open EchoGPT website 2. Click on API Platform link 3. Redirect to Developer page 4. Click on Login button 5. Click on Sign Up 6. Enter Name, Email, Phone, Password 7. Click on 'Sign Up' | Name: Nasir Email: nasir@test.com Phone: 017XXXXXXXX Password: Test@123 | User should be successfully registered and redirected to the Developer Platform dashboard | User account created successfully and Developer Platform opened | Medium | Minor | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_DEV_NEG_001 | (TS_009) Register Functionality | Sign up should fail with invalid email | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT website 2. Go to API Platform 3. Go to Developer page 4. Click Login → Sign Up 5. Enter all valid data except email 6. Click Submit | Name: Nasir Email: nasir@123 Phone: 017XXXXXXXX Password: Test@123 | System should show proper error message like “Please enter a valid email address” and should not allow sign up | Warning messages were displayed as per the Email . | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_DEV_NEG_002 | (TS_009) Register Functionality | Sign up should fail when required fields are empty | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT website 2. Go to API Platform 3. Go to Developer page 4. Click Login → Sign Up 5. Keep Name/Phone/Password empty 6. Click "Sign Up' | Name: (Blank) Email: nasir@gmail.com Phone: (Blank) Password: (Blank) | System should show validation message for each required field and should not create account | User account created successfully and Developer Platform opened | High | Major | Fail | ECHOGPT_BUG_007 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_DEV_NEG_003 | (TS_009) Register Functionality | Sign up should work with valid phone number | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid Name, Email, Phone, Password 5. Click "Sign Up' | Phone: 01712345678 | Account should be created successfully and user should enter Developer Platform | User account created successfully and Developer Platform opened | Medium | Minor | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_DEV_NEG_004 | (TS_009) Register Functionality | System should not accept short phone number | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid data except Phone 5. Click "Sign Up' | Phone: 0171234 | System should show error like “Enter a valid phone number” | User account created successfully and Developer Platform opened | Medium | Minor | Fail | ECHOGPT_BUG_008 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_DEV_NEG_005 | (TS_009) Register Functionality | System should not accept special characters | 1. User must be on EchoGPT Developer Sign Up page 2. Internet connection active | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid data except Phone 5. Click "Sign Up' | Phone: 01712@#678 | System should show error like “Enter a valid phone number” | User account created successfully and Developer Platform opened | Medium | Minor | Fail | ECHOGPT_BUG_009 | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-05-12
TC_LOGIN_001 | (TS_010) Login Functionality | User should be able to sign in with existing account | 1. User account must already be created 2. User must be on EchoGPT Login page 3. Internet connection active | 1. Open EchoGPT website 2. Go to API Platform → Developer Page 3. Click on Login 4. Enter valid Email and Password 5. Click on Sign In button | Email: nasir@test.com Password: Test@123 | User should be successfully logged in and redirected to Developer Platform dashboard | 1. User is navigated to Login page | High | Major | Pass |  | Device: Windows PC OS: Windows 10 (64-bit) Browser: Chrome /Edge | 2025-06-12
TC_AppTestingService_Install_001 | (TS_011) Verify app installation from Play Store | App should install successfully | 1. Internet connection must be active 2. User must be logged into Play Store | 1. Open Play Store 2. Search the App Testing Service app 3. Click Install | Not Applicable | App should be downloaded and installed successfully without any error | App install successfully | High | Major | Pass |  | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_APP_002 | (TS_011) Verify app launch after installation | App should not crash on launch | 1. App must be installed successfully | 1. Tap on app icon from home screen | Not Applicable | App should open without crashing | App open without crashing | High | Major | Pass |  | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_APP_003 | (TS_012) Verify first screen loading after app launch | First screen should load properly | 1. App must be installed 2. App must open successfully | 1. Open the app 2. Observe the first screen UI | Not Applicable | First screen should load fully without blank screen, delay, or UI break | First screen load fully without blank screen, delay, or UI break | High | Major | Pass |  | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_APP_SIGNUP_001 | (TS_013) Verify email field input behavior during sign up | Email input is hidden and automatically filled in password field | 1. User must be on Sign Up page 2. Internet connection active | 1. Open the app/website 2. Go to Sign Up page 3. Click on Email Address field 4. Type a valid email 5. Observe Email field and Password field | Email: nasir@test.com | Email field should display normal text (not masked) and password field should remain empty until user types password manually | Email field shows dots (●●●) like password and the same email is automatically filled into the password field | High | Major | Fail | APPTESTINGSERVICE_BUG_010 | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_APP_LOGIN_001 | (TS_014) Verify login after manual vs Google sign up | Manual sign up credentials fail to login, Google sign up works | 1. User has manually created account 2. User has Google account sign up 3. Internet connection active | 1. Open app/website 2. Click Login 3. Enter Email + Password from manual sign up 4. Click Sign In 5. Observe result 6. Logout 7. Try login with Google sign up credentials | Manual: Email: zzzz@gmail.com ,Password: 12345 Google: Email: nasir@gmail.com | Manual sign up credentials should login successfully; Google sign up credentials should login successfully | Manual sign up credentials show “Invalid Credentials”; Google sign up credentials login successfully | High | Major | Fail | APPTESTINGSERVICE_BUG_011 | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_APP_LOGIN_001 | (TS_014) Verify behavior when Google login cancelled | Canceling Google login causes black screen / UI freeze | 1. App installed and on Login page 2. Internet connection active 3. At least one Google account available on device | 1. Open app/website 2. Navigate to Login page 3. Click on Google Login button 4. Google account window appears 5. Press back / cancel without selecting any email 6. Observe UI | Not Applicable | App should return to normal login UI without freeze or black screen | Login UI turns black immediately after cancelling Google login | High | Major | Fail | APPTESTINGSERVICE_BUG_012 | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_Echo_INSTALL_01 | (TS_014) Verify app installation from Play Store | App should install successfully | 1. Internet connection must be active 2. User must be logged into Play Stor | 1. Open Play Store 2. Search EchoGPT app 3. Click Install | Not Applicable | App should be downloaded and installed successfully without any error | App downloaded and installed successfully without any error | High | Major | Pass |  | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_LAUNCH_01 | (TS_015) Verify app stability on first launch | App should not crash on first launch | App installed successfully, Internet active | 1. Tap on EchoGPT app icon 2. Observe app behavior on launch | Not Applicable | App should open successfully without crashing | App open successfully without crashing | High | Major | Pass |  | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12
TC_SPLASH_01 | TS_016) Verify first screen loads correctly | Splash / First screen should load without issues | App installed successfully, App launches without crash | 1. Launch app 2. Observe Splash screen and first screen load 3. Check UI elements properly displayed | Not Applicable | Splash screen and first screen should load fully without blank screen, delay, or broken UI | Splash screen and first screen loaded fully without blank screen, delay, or broken UI | High | Major | Pass |  | Device: Medium Phone (Emulator) OS: Android API 36 App Version: | 2025-06-12

## Bug Reports
Bug ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot | Logs
APPTESTINGSERVICE_BUG_001 | Validate 'Thank you for registering' email is sent to the registered email address as a confirmation for registering the account | 1. Click on 'Log In' 2. Click on 'Create Account' option 3. Enter new Account Details into the Mandatory Fields (First Name, Last Name, E-Mail,phone, Password 4. Click on 'Create account' button . | 1. Validate a confirmation email for registering the account is sent to the registered email address. | 1. User has not received any email to his registered email address | Major | Medium
APPTESTINGSERVICE_BUG_002 | Validate proper notification messages are displayed for the mandatory fields, when you don't provide any fields in the 'Create account' Page | 1. Click on 'Log in' button2. Click on 'Create account' option 3. Don't enter anything into the fields 4. Click on 'Create account' button | 1. The below warning messages should be displayed for the respective fields: For First Name field, the warning message 'First Name must be between 1 and 32 characters!' should be displayed For E-Mail field, the warning message 'E-Mail Address does not appear to be valid!' should be displayed For phone field, the warning message 'phone must be between 3 and 32 characters!' should be displayed For Password field, the warning message 'Password must be between 4 and 10 characters!' should be displayed | Warning messages were displayed as per the Email and Password, but no validation was applied to the Name and Phone Number fields. | Major | Medium
APPTESTINGSERVICE_BUG_003 | Verify Profile page opens correctly | 1. Login to app 2. Click on profile icon (top right) 3. Click on “Profile” | Profile page should open successfully without any error | 404 Page Not Found displayed | Major | High
APPTESTINGSERVICE_BUG_004 | Verify "App Package" external link opens valid destination | 1. Login to the system 2. Go to Dashboard 3. Click on View Sample Dashboard / App Details 4. Scroll to App Package section 5. Click on the package link (com.vanti.mealchaos) | User should be redirected to the correct app details page or external Play Store link in a new tab | App Package link does not respond / no redirection happens | Minor | Low
ECHOGPT_BUG_005 | Verify user can generate image after providing prompt | 1. Open EchoGPT website 2. Sign in with valid credentials 3. Go to Image generation section 4. Enter valid prompt in image input field 5. Click Generate button | System should generate the image corresponding to the entered prompt | System shows error: “failed to generate image try again” | Major | High
ECHOGPT_BUG_006 | EchoGPT stops responding after multiple messages | 1. Open EchoGPT website/app 2. Login with valid account 3. Start a new chat 4. Send multiple messages continuously for some time 5. Send another new message | EchoGPT should respond to every message without stopping | After some time, EchoGPT does not respond to new messages at all | Major | High
ECHOGPT_BUG_007 | Sign up should fail when required fields are empty | 1. Open EchoGPT website 2. Go to API Platform 3. Go to Developer page 4. Click Login → Sign Up 5. Keep Name/Phone/Password empty 6. Click "Sign Up' | System should show validation message for each required field and should not create account | User account created successfully and Developer Platform opened | Major | High
ECHOGPT_BUG_008 | System should not accept short phone number | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid data except Phone 5. Click "Sign Up' | System should show error like “Enter a valid phone number" | User account created successfully and Developer Platform opened | Minor | Medium
ECHOGPT_BUG_009 | System should not accept special characters | 1. Open EchoGPT 2. Go to API Platform → Developer Page 3. Click Login → Sign Up 4. Enter valid data except Phone 5. Click "Sign Up' | System should show error like “Enter a valid phone number" | User account created successfully and Developer Platform opened | Minor | Medium
APPTESTINGSERVICE_BUG_010 | Email input is hidden and automatically filled in password field | 1. Open the app/website 2. Go to Sign Up page 3. Click on Email Address field 4. Type a valid email 5. Observe Email field and Password field | Email field should display normal text (not masked) and password field should remain empty until user types password manually | Email field shows dots (●●●) like password and the same email is automatically filled into the password field | Major | High
APPTESTINGSERVICE_BUG_011 | Manual sign up credentials fail to login, Google sign up works | 1. Open app/website 2. Click Login 3. Enter Email + Password from manual sign up 4. Click Sign In 5. Observe result 6. Logout 7. Try login with Google sign up credentials | Manual sign up credentials should login successfully; Google sign up credentials should login successfully | Manual sign up credentials show “Invalid Credentials”; Google sign up credentials login successfully | Major | High
APPTESTINGSERVICE_BUG_012 | Canceling Google login causes black screen / UI freeze | 1. Open app/website 2. Navigate to Login page 3. Click on Google Login button 4. Google account window appears 5. Press back / cancel without selecting any email 6. Observe UI | App should return to normal login UI without freeze or black screen | Login UI turns black immediately after cancelling Google login | Major | High

## Exploratory Testing Notes
Exploratory Testing Summary - 40 min session Session ID: ET-2025-12-05-01 Tester: Nasir Ahmed Date: 2025-12-05 Duration: 40 minutes Scope: Android Apps: EchoGPT (com.echogpt.chatapp), AppTestingService (com.apptestingservice) Websites: echogpt.live, apptestingservice.com Environment: Devices: Medium_Phone_API_36.1,Desktop Network: Wi‑Fi, 4G LTE Browsers: Chrome 120 (Android/Desktop), Firefox 121 (Desktop) Accessibility Tools: Android,Chrome DevTools Accessibility panel Security Tools: Chrome DevTools Perspective 1 -EchoGPT Android App Focus: Messaging/AI chat, login, UI/UX, stability Charters: C1. Onboarding/Auth Fresh install -> first launch ->sign-up/login Findings: Login button enabled even during network loss -> spinner persists >30s Email/password validation delayed -> inline feedback missing C2. Core Features Chat compose/send, large input (>3,000 chars), rapid consecutive sends Findings: UI freezes 3–5s on very large input Rapid sends cause duplicate message render; scroll jumps C3. UI/UX & Responsiveness Orientation change, input field layout, dark mode Findings: Landscape truncates input; send icon overlaps placeholder C4. Accessibility TalkBack, focus traversal, content description Findings: Send button lacks descriptive label C6. Stability Background/foreground, scroll retention Findings: Scroll position occasionally lost after resume Evidence: screenshots + recordings/logs Perspective 2 - AppTestingService Android App Focus: Content browsing, filtering, auth, stability Charters: C1. Onboarding/Auth Sign-up/login flows Findings: Validation delayed on email Password reset success message generic C2. Core Features List navigation, filtering, search Findings: Filter resets after navigation -> state not persisted C3. UI/UX Font scaling, icon sizing Findings: Icons clipped at 200% font size C4. Accessibility Focus order, keyboard nav Findings: Focus skips filter chip -> inconsistent keyboard navigation C6. Stability ANR/lag under weak network Findings: Brief ANR (~1s) after filter apply Evidence: Perspective 3 - echogpt.live Website Focus: Web UI, chat, security, accessibility Charters: C1. Onboarding/Auth Login/sign-up flows, social login Findings: Password reset flow success message generic C3. UI/UX & Responsiveness Dark mode, contrast, layout Findings: Secondary text contrast below WCAG AA in dark mode C4. Accessibility Focus indicators, modals Findings: Modal traps focus, no visible indicator for close C5. Security Mixed content, certificate validation Findings: Loads HTTP image -> mixed content warning Evidence: Perspective 4 - apptestingservice.com Website Focus: Web content, filtering, error handling, security Charters: C2. Core Features List navigation, filtering/search Findings: Filter resets after navigation -> usability issue C5. Security Error handling / information disclosure Findings: 5xx error returns verbose stack trace -> info leak C6. Stability Stress/load testing Findings: No hard crashes, minor jank on filter apply Evidence: Time Log (40 min) Charter Duration Setup 03m C1 Onboarding/Auth 08m C2 Core Features 09m C3 UI/UX 07m C4 Accessibility 06m C5 Security 04m C6 Stability 03m

## Short Summary Report
SHORT SUMMARY REPORT Project: EchoGPT & AppTestingService (Android Apps + Websites) Tested By: Nasir Ahmed Platforms Covered: Android App: EchoGPT Android App: AppTestingService Website: echogpt.live Website: apptestingservice.com TESTING OVERVIEW A full test cycle was performed on two Android applications and two websites. The testing included: Functional Testing UI Testing Exploratory Testing Security & Validation Testing Accessibility & Negative Testing 1.MAJOR ISSUES FOUND (HIGH IMPACT) A. EchoGPT Android App (High Risk): Image generation completely not working. Error shown every time user tries to generate image. Chat system becomes unresponsive after a few messages. Response speed is very slow initially and later stops fully. Android app also stops responding during normal chat. Severe stability issue found. B. EchoGPT Website (High & Medium Risk): Signup allows space in name, phone, and password fields. No proper validation for phone number length. No error message shown for invalid input. This creates serious security and data integrity risks. C. AppTestingService Website (High Risk): Profile section opens a “404 Page Not Found” error. Signup form accepts only space as input. Phone number field has no character limit or validation. App submission flow is broken: Poor sequence of page links User cannot return to previous page normally Payment process sometimes fails with error. D. AppTestingService Android App (High Risk): Google login -> when user presses back, screen turns fully black. App performance is slow. Similar payment-related errors as website. 2.SEVERITY & RISK SUMMARY High Severity Bugs: Image generation failure Chat system freeze 404 profile page Broken payment flow Black screen after Google login Medium Severity Bugs: Very slow response Broken navigation flow Weak form validations Overall Product Risk Level: HIGH 3.STABILITY & USER EXPERIENCE STATUS Both apps feel unstable. Users cannot rely on chat or core services. App freezing and black screen issues can cause user drop. Slow performance creates poor user experience. 4.SECURITY & VALIDATION STATUS Forms accept space as valid input. No phone number length validation. No proper error messages. These allow fake data submission and create serious security concerns. 5.RELEASE READINESS Current build is NOT READY for production release because: Core features are broken (chat, image generation, payment). Major validation gaps exist. Stability issues found in both apps. 404 and broken navigation observed. 6.FINAL RECOMMENDATIONS Before next release, the following must be fixed: Fix image generation API and chatbot freezing issue. Improve app performance and response speed. Add strong validation for: Name Phone number Password Fix 404 profile issue. Improve app submission navigation flow. Fully stabilize payment system. Fix black screen issue after Google login.